## Defects
Defect Tracker – AI-Powered Workforce Analytics & Talent Intelligence Dashboard | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Team Member 2 | 2026-08-03 | Duplicate employee records appeared after importing sample workforce data | SPRINT 1 | ameer,jagruthi,anuja | Logical | Added duplicate detection and unique employee-ID validation | 2026-08-04 | Closed | Retested with duplicate records
2 | Team Member 1 | 2026-08-10 | Employee API returned incomplete department data for some records | SPRINT 1 | teja,harika | Logical | Corrected database join/query mapping and retested endpoint | 2026-08-13 | Closed | API response validated
3 | Team Member 3 | 2026-08-19 | Attrition model produced null risk score for records with missing optional fields | SPRINT 2 | anil | Logical | Added preprocessing/default handling for missing values | 2026-08-22 | Closed | Model service retested
4 | Team Member 1 | 2026-08-27 | Dashboard chart did not refresh after changing department filter | SPRINT 2 | mahek,aishwarya | User Interface | Updated filter state handling and API refresh logic | 2026-08-28 | Closed | Verified across multiple departments
5 | Team Member 4 | 2026-09-04 | KPI totals differed from manually calculated sample values | SPRINT 3 | mahalaxmi | Logical | Corrected turnover calculation and added unit test coverage | 2026-09-04 | Closed | Sample calculations matched
6 | Team Member 4 | 2026-09-10 | Long employee names were truncated in dashboard table | SPRINT 3 | aman,sindhura | User Interface | Adjusted column sizing and text wrapping | 2026-09-11 | Closed | Verified with long-name test data

## Sheet2
Logical
User Interface
Maintainability
Standards
Others